Call forward sheet

Site address:	16 Breaville Close, Breaville	Project no:	246
Client:	David and Jo Smith	Building surveyor:	Bob Brown
Contact no:	8765 4319	Office number:	8009 3211

|  |  |  | Ordering |  | Supplier details |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Task/activity | Order no. | Order day | Delivery date | Material supplier | Contractor | Supplier contact no. | Instructions or comments |
| Base stage |  |  |  |  |  |  |  |  |
| 21 | Order toilet | 100100 | 10/11/07 | 15/11/07 |  | Hire Me | 9847 7788 | Emptied weekly. Call for unscheduled service. |
| 22 | Order crossover | 100105 | 10/11/07 | 15/11/07 |  | Hire Me | 9847 7788 |  |
| 23 | Order temporary fencing | 100106 | 10/11/07 | 16/11/07 |  | Melbourne Temp Fencing | 9587 5547 |  |
| 24 | Earthworks | 100109 | 3/11/07 | 18/11/07 |  | Jack Excavations | 8745 1154 |  |
| 25 | Prepare flooring | 100110 | 15/11/07 | 18/11/07 |  | Carpenters R Us | 9536 4780 |  |
| 26 | Stormwater rough in | 100111 | 3/11/07 | 19/11/07 |  | Paul’s Plumbing | 9854 4547 |  |
| 27 | Under slab sewer | 100112 | 8/11/07 | 19/11/07 |  | Paul’s Plumbing | 9854 4547 |  |
| 28 | Order timber | 100114 | 3/11/07 | 18/11/07 | Timber Specialists |  | 9541 1111 |  |